## TAX BE Issuer
Priority | TEST Case | ETA | Main Topic | Functionality | Application | User Profile | Pre-requisites | Dependencies | References | Description | Expected Result | Testing status | Testing Comments | Last Day Execution | BUG Ref
Test relevance | Numerical ID of the test case | Planned date for completion | General topic object of the test case | Specific functionality of the test case | Application or module being tested | Type of client targeted by the test case | Conditions or setup needed before testing | Tests or systems that must be completed first | Related documents or requirements | Detailed description of the test case | Anticipated outcome of the test | Specify test outcome | Report notes / comments if needed | Specify test execution date | Identifier for any bugs found
High Priority | BO-PROF-001 |  | BO CREATION & PROFILING | Client to create BO profiles by uploading excel file in Acupay 4 | [5 empty] | BO profiles correctly created | BO profiles created and ready for tax docs upload | To Do | In case no client is available this step can be performed internally
High Priority | BO-PROF-002 |  | BO CREATION & PROFILING | Client to upload PDF (fake) of tax docs | [5 empty] | BO ready to get payments at expected tax rate | BO documented for expected rate (15% or whatever) | To Do | In case no client is available this step can be performed internally
High Priority | BO-PROF-003 |  | TAX DOCS DELIVERY | Client to send hard copy of tax docs (simulation) | [5 empty] | Docs ready for shipping by the expected deadline | Hard copy received and ready to be shipped to the Belgian issuer | To Do | This step is simulated by Tax Operations
High Priority | TC-DVCA-001 |  | DVCA BE ISIN | Tax Breakdown upload by client at RD | [5 empty] | Tax Breakdown rejected (if incorrect) or processed (if correct) | Client to upload Tax Breakdown CERT (excel file) in Acupay system at record date within given timeline | To Do | In case no client is available this step can be performed internally
High Priority | TC-DVCA-002 |  | DVCA BE ISIN | SWIFTs for Tax breakdown on DVCA MAND | [5 empty] | - Accept the MT565 tax breakdown instruction; OR - Reject the MT565 tax breakdown instruction (in case of rejection Operations can adjust manually in Megacor as contingency) | 1. MT565 (Swift 15022) for tax breakdown sent by Acupay on the morning of PD to Megacor 2. MT567 (Swift 15022) that Megacor will send to Acupay to reply | To Do
High Priority | TC-DVCA-003 |  | DVCA BE ISIN | Tax Breakdown upload by client after RD for Reversal | [5 empty] | Tax Breakdown rejected (if incorrect) or processed (if correct) | Client to upload Tax Breakdown REVE (excel file) in Acupay system after pay date within given timeline | To Do | In case no client is available this step can be performed internally
High Priority | TC-DVOP-001 |  | DVOP BE ISIN | Tax Breakdown upload by client at RD | [5 empty] | Tax Breakdown rejected (if incorrect) or processed (if correct) | Client to upload Tax Breakdown CERT (excel file) in Acupay system at record date within given timeline | To Do | In case no client is available this step can be performed internally
High Priority | TC-DVSE-001 |  | DVSE BE ISIN | Tax Breakdown upload by client at RD | [5 empty] | Tax Breakdown rejected (if incorrect) or processed (if correct) | Client to upload Tax Breakdown CERT (excel file) in Acupay system at record date within given timeline | To Do | In case no client is available this step can be performed internally
High Priority | TC-TREP-001 |  | TAX REPORTING | Generation of Tax Reporting by Acupay | [5 empty] | Tax Report to be sent to the issuer in line with guidelines and correct in terms of expected content | Download from Acupay of tax reporting and verify to be correct | To Do | This step is done by Tax Operations