## Portfolio Transfer for Bearer
Ref_Key | Priority | Test Design Status | TEST Case | ETA | Main Topic | Functionality | Application | Role / User Profile | Pre-requisites | Dependencies | References | Description | Expected Result | Testing status | Testing Comments | Last Day Execution | BUG Ref
| Test relevance |  | Numerical ID of the test case | Planned date for completion | General topic object of the test case | Specific functionality of the test case | Application or module being tested | Type of client targeted by the test case | Conditions or setup needed before testing | Tests or systems that must be completed first | Related documents or requirements | Detailed description of the test case | Anticipated outcome of the test | Specify test outcome | Report notes / comments if needed | Specify test execution date | Identifier for any bugs found
High Priority/Approved by PO | High Priority | Approved by PO | PT_1 | 2026-07-31 | Cross-CSD MOTI-SICV | Settlement of Cross-CSD transactions with FR instruments |  | ICP or DCP (if they want to use the bulk upload file) |  |  |  | 1. Create OTC delivery instruction in the other CSD; 2. Create corresponding receive instruction using the bulk upload file or instruct directly in ES-MIL; 3. Ensure both instructions are matched and settled; 4. Ensure postions are correctly generated in ES-MIL books. |  | To Do
High Priority/Approved by PO | High Priority | Approved by PO | PT_2 | 2026-07-31 | Cross-CSD MOTI-NECI | Settlement of Cross-CSD transactions with NL instruments |  | ICP or DCP (if they want to use the bulk upload file) |  |  |  | 1. Create OTC delivery instruction in the other CSD; 2. Create corresponding receive instruction using the bulk upload file or instruct directly in ES-MIL; 3. Ensure both instructions are matched and settled; 4. Ensure postions are correctly generated in ES-MIL books. |  | To Do
High Priority/Approved by PO | High Priority | Approved by PO | PT_3 | 2026-07-31 | Cross-CSD MOTI-CIKB | Settlement of Cross-CSD transactions with BE instruments |  | ICP or DCP (if they want to use the bulk upload file) |  |  |  | 1. Create OTC delivery instruction in the other CSD; 2. Create corresponding receive instruction using the bulk upload file or instruct directly in ES-MIL; 3. Ensure both instructions are matched and settled; 4. Ensure postions are correctly generated in ES-MIL books. |  | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_4 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_5 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_6 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_7 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_8 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_9 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_10 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_11 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_12 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_13 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_14 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_15 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_16 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_17 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_18 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_19 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_20 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_21 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_22 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_23 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_24 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_25 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_26 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_27 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_28 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_29 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_30 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_31 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_32 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_33 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_34 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_35 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_36 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_37 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_38 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_39 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_40 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_41 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_42 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_43 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_44 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_45 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_46 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_47 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_48 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_49 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_50 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_51 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_52 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_53 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_54 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_55 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_56 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_57 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_58 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_59 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_60 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_61 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_62 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_63 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_64 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_65 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_66 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_67 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_68 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_69 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_70 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_71 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_72 | [10 empty] | To Do
Not to be tested/Under Construction | Not to be tested | Under Construction | NAME_73 | [10 empty] | To Do